# Crop-MATCHING Kick-off Meeting

# Thessaloniki 6th – 7th November 2025

Meeting venue: Mediterranean Palace Hotel, Salaminos 3, Karatasou str, 54626 Thessaloniki

(Google maps) (Room POSIDON B)

# Agenda

First day: “Imminent Tasks for the first Reporting Period M1-M18”

| 6th November 2025 |  |  |
| --- | --- | --- |
| Time (EEST) | Description | Presenter |
| Chairman: Filippo Arfini |  |  |
| 9:00 – 9:15 | Opening and welcome, Project Outlook by the Coordinator Prof. Konstadinos Mattas | AUTH |
| 9:15 – 9:35 | EU Project Officer welcome speech by Mr Tiago Freitas | Tiago Freitas |
| 9:35 – 9:50 | Brief presentation on the policy context from DG AGRI by Gisela Quaglia | Gisela Quaglia |
| 9:50– 10:10 | Briefing by AUTH RC officer οn, - Financial management procedures for European projects - Support and clarifications for project partners - Guidelines for compliance with HORIZON rules | AUTH |
| 9:35 – 10:30 | Partners presentation (3 min max. each) - Group introduction – Major role in the project | All partners |
| 10:30 – 11:10 | WP1. Requirements elicitation [WP Leader: UNIPR] - Task 1.1 Multi-actor co-creation community (Task Leader: BIOAZUL) (M1-M18) - Task 1.2: Review of existing knowledge (Task Leader: AUP) (M1-M10) - Task 1.3: Selection of high potential lighthouse crop matching practices (Task Leader: UNIPR) (M7-M14) - Task 1.4: Validation of lighthouse crop matching practices and selection of success stories (Task Leader: AUTH) (M10-M18) | Presenters: BIOAZUL AUP UNIPR AUTH |
| 11:00 – 11:30 | Coffee break |  |
| 11:30 – 12:00 | WP2. Information and training needs analysis [WP Leader: EGE] - Task 2.1: Smallholder farmers’/foresters’ information and training needs analysis (Task Leader: EGE) (M8-M18) - Task 2.2: Policy and governance needs analysis (Task Leader: CIHEAM/MAICH) (M8-M18) | Presenters: EGE CIHEAM/MAICH |
| 12:00– 12:30 | WP8. Communication and capacity building [WP Leader: NIBIO] - Task 8.1 Communication activities (Task Leader: NIBIO) (M1-M18) - Presentation of the website and social media channels (NWARE) | Presenters: NIBIO NWARE |
| 12:30 –13:30 | WP11-WP13. Project Management [WP Leader: AUTH] - Administrative info, Internal communication (e-platform, mailing), Presentation of the Redmine platform (storage tool) (AUTH) - Task 11.1: Ethics requirements (Task Leader: NIBIO) (M1-M12) - Managerial Highlights (W11-WP13) (WPs Leader: AUTH) (M1-M48) | Presenters: AUTH NIBIO |
| 13:30 – 14:15 | Working Lunch |  |
| 14:15 – 15:00 | Discussions (summary, organisational issues) | All partners |
| 19:00 | Dinner at “Loupino Restaurant”, Katouni 4, Google maps |  |

# Agenda

Second day: “WPs overview M19-M48 and Management structure”

| 7th November 2025 |  |  |
| --- | --- | --- |
| Time | Description | Presenter |
| Chairman: Matthew Gorton |  |  |
| 9:00 – 09:20 | WP3. Analysis of selected success stories [WP Leader: UNEW] - Task 3.1 Cost-benefit analysis of success stories (Task Leader: UNEW) (M19-M30) - Task 3.2: Information package preparation (Task Leader: PFATC) (M19-M30) - Task 3.3: E-learning training package preparation (Task Leader: PRISM) (M24-M30) | Presenter: UNEW |
| 09:20 – 09:40 | WP4. Crop-MATCHING digital cloud solution [WP Leader: PRISM] - Task 4.1 Design and development of the Crop-MATCHING online platform (Task Leader: PRISM) (M19-M30) - Task 4.2 Design and development of the Service E-Learning course (Task Leader: NWARE) (M24-M36) | Presenter: PRISM |
| 09:40 – 10:00 | WP5. CROP-MATCHING personalized mechanisms [WP Leader: NWARE] - Τask 5.1 Crop-MATCHING personalization mechanisms (Task Leader: NWARE) (M37-M42) - Task 5.2 Final version of the Service E-Learning course (Task Leader: NWARE) (M40-M42) | Presenter: NWARE |
| 10:00 – 10:20 | WP6. Make success stories easily accessible [WP Leader: F4S] - Τask 6.1 Easily accessible success stories (Task Leader: F4S) (M19-M36) - Task 6.2 First cross-fertilization event (Task Leader: PRISM) (M30-M36) | Presenter: F4S |
| 10:20 – 10:40 | WP7. Inspiring communication of success stories [WP Leader: S&C] - Τask 7.1 Inspiring communication of success stories (Task Leader: S&C) (M37-M42) - Task 7.2 Second cross-fertilization event (Task Leader: AUP) (M37-M42) - Task 7.3: Social norms campaign (Task Leader: S&C) (M37-M46) | Presenter: S&C |
| 10:40 – 11:10 | Coffee break |  |
| 11:10 – 11:30 | WP9. Communication and capacity building [WP Leader: BIOAZUL] - Τask 9.1 Networking (Task Leader: BIOAZUL) (M19-M36) | Presenter: BIOAZUL |
| 11:30 – 11:50 | WP10. Communication and capacity building [WP Leader: PFATC] - Τask 10.1 Dissemination and exploitation activities (Task Leader: PFATC) (M37-M48) | Presenter: PFATC |
| 11:50 – 13:00 | Management and Organisational structure - Organisational structure - General Assembly (GA): Appoint a representative per partner - Executive Management Board (EMB): Appoint a representative per partner (only for WP leaders) - Data Protection Officer (DPO): Appoint a representative per partner - Dissemination Manager: Appoint a representative per partner - Main contact: Appoint the person who will be the main point of communication - Meetings arrangements | All partners |
| 13:00 – 13:45 | Discussions (summary, organisational issues) | All partners |
| 13:45 – 14:30 | Lunch and end of the meeting |  |